## Slide 1: BUSINESS REVIEW REPORT

## Slide 2: Project Scope & Current Status
CRITICAL REQUIREMENT: Phases 1, 2, and 3 complete by December 2025
Overall Progress: ~20% Complete across all phases(Still working on dev and prod not yet started)
Timeline: EXTREMELY AGGRESSIVE - Requires Parallel Execution
Key Challenge: Network/ Internet Connectivity + Many Major Components are still InProgress. (Due to security restrictions and Procedures)

## Slide 3: Phase 1 Completion Plan - WHERE & HOW & WHEN
AWS Infrastructure
Development Environment
50% complete
✅ VPC and CIDR configuration
✅ DevOps account setup
✅ Security groups and networking
❌ Production not yet started
GitHub Enterprise
Development Environment
40% complete
✅ Primary Server Installation
✅ Replica Server Setup
✅ Backup Server Infrastructure
❌ TLS Certificate and AD integration
❌ Production not yet started
JFrog Artifactory & Xray
Development Environment
30% complete
✅ EKS 6-node cluster setup with RDS
✅ DNS Resolver connectivity resolved
⏳ Basic cluster addons installation
❌ On-Prem JFrog Connectivity (BLOCKER)
❌ Production not yet started
OpenSearch
❌ Development not yet started
❌ Production not yet started
Grafana
❌ Development not yet started
❌ Production not yet started
Data migration from onprem to AWS
❌ Production not yet started
Pipeline integration
❌ EKS GitHub runners setup
❌ CI/CD pipeline setup
❌ GitHub Actions integration
❌ Development not yet started
❌ Production not yet started
Key challenges
Networking issue
  DNS resolver issue – (resolved)
  Requires workaround for all external dependencies.
  Production AWS account not yet ready
  AD integration configuration for Github server waiting identity team
  Data Migration flow not finalized
Completion Timeline (Including Production)
AWS Infrastructure - Sep 15
GitHub Enterprise - Sep 22
JFrog Artifactory & Xray. - Sep 26
OpenSearch - Sep 26
Grafana - Sep 26
Data migration from onprem to AWS – Oct 7th
Pipeline integration – Oct 7

## Slide 4: Phase 2 Planning - WHAT'S NEXT & WHEN
Jira(SaaS) integration with GitHub(AWS)
ServiceNow(SaaS) integration with GitHub(AWS)
DAST tool integration
Security tool integration
PaC for IaC tool integration
Pipeline documentations
Estimated start time would be October 2nd week

## Slide 5: Phase 2: Key Challenges and Support
Phase 2 involves lot of tools integration. So, below are the challenges that we see and support needed.
Challenges:
External team dependencies takes longer time to resolve.
Network restriction forcing us to look for workaround.
Support:
Enabling internet access by inspection accounts.
Accelerating external team dependencies.